## Sheet1
Q type | Level | Category | Skill | SubSkill | Topic | Q text | Option/ Answer 1 | Option/ Answer 2 | Option/ Answer 3 | Option/ Answer 4 | Option/ Answer 5 | Option/ Answer 6
Single | Simple | Code | V&V - Automation Testing | Agile | Extreme Programming (XP),Lean Software Development & Kanban | An organization need to select one of the Agile type which will help bringing the whole team together in the presence of simple practices, with enough feedback to enable the team to see where they are and to tune the practices to their unique situation. Which technique they should opt. | Kanban | Exteam Programing | Scrum | Lean Software Development
Single | Simple | Concept | V&V - Automation Testing | Agile | Agile Methods and Practices - SCRUM | Who plays the role of team in Scrum | The person who creates an optimal working-condition for the team and is responsible for this condition to be retained | The person who is responsible for implementing the functionality through the delivery of the product | The person who serves as an interface between the team and other involved parties | The person who is Responsible for implementing practices and rules and ensuring that it is followed
Multiple | Medium | Concept | V&V - Automation Testing | Agile | Agile Process Framework | When to use Agile Model | For small projects where requirements are fixed | For mission criticle projects where testing is of high importance | When limited planning is acceptable | When new changes must be implimeted
Single | Medium | Code | V&V - Automation Testing | Agile | Agile Testing Quadrants and Agile Test Planning | Consider the following scenario with respect to Agile testing: An Agile testing is conducted which focuses on Business facing tests that supports the team,Functional Tests Examples Story Tests Prototypes Simulations. To which Testing quadrant the mentioned scenario belong to? | Quadrant1 | Quadrant 2 | Quadrant 3 | Quadrant 4
Single | Complex | Concept | V&V - Automation Testing | Agile | Introduction to Agile Testing | To which category of Agile values following scenario belong to: The best developers understands that , their customers, and in fact all project stakeholders also have their own areas of expertise and have value to add to a project. An effective approach is to assume that everyone involved with your project has equal value and therefore should be treated with respect. | Communication | Courage | Feedback | Humanity
Single | Simple | Code | V&V - Automation Testing | Agile | Agile Methods and Practices | Consider the following scenario: The organization has to decide on selecting one of the Agile practise. Due to time constraints the goals are to develop software in one-third the time, with one-third the budget, and with one-third the defect rate. Which Agile practise the organisation should go for? | Scrum | Extreme Programing | Lean Software Development | Kanban
Single | Simple | Concept | V&V - Automation Testing | Agile | Agile Process Framework | In Agile foundation what is Agility | Creating small increments of the software system which is delivered as a series of time boxed iterations. | Is inevitable and important to be taken care of. | The ability to respond quickly. | With the help of constant discussions & workshops aimed at information exchange between customer & team.
Single | Medium | Code | V&V - Automation Testing | Agile | Agile Testing Quadrants and Agile Test Planning | Match the following Agile testing quadrants with the type of testing in the respective quadrants. 1.Quadrant 1 2..Quadrant 2 3..Quadrant 3 4. .Quadrant 4 A.Performance Testing,Load testing,Stress Testing. B.Story Test ,Prototypes C. Unit Testing D.Exploratory Testing, Usability Testing | Quadrant 1---Performance Testing,Load testing,Stress Testing. Quadrant 2---Exploratory Testing, Usability Testing Quadrant 3---Story Test ,Prototypes Quadrant 4---Unit Testing | Quadrant 1--- Exploratory Testing, Usability Testing Quadrant 2--- Unit Testing Quadrant 3---Story Test ,Prototypes Quadrant 4---Performance Testing,Load testing,Stress Testing. | Quadrant 1--- Unit Testing Quadrant 2---Story Test ,Prototypes Quadrant 3---Exploratory Testing, Usability Testing Quadrant 4---Performance Testing,Load testing,Stress Testing. | Quadrant 1---Story Test ,Prototypes Quadrant 2---Unit Testing Quadrant 3---Performance Testing,Load testing,Stress Testing. Quadrant 4---Exploratory Testing, Usability Testing
Multiple | Medium | Concept | V&V - Automation Testing | Agile | Agile Methods and Practices - SCRUM | Who plays the role of Scrum Master in Scrum | The person who creates an optimal working-condition for the team and is responsible for this condition to be retained | The person who is responsible for implementing the functionality through the delivery of the product | The person who serves as an interface between the team and other involved parties | The person who is Responsible for implementing practices and rules and ensuring that it is followed
Single | Complex | Concept | V&V - Automation Testing | Agile | Introduction to Agile Testing | Which of the four testing quadrants focuses on Technology facing tests that support the team Unit Tests Component Tests | Quadrant1 | Quadrant2 | Quadrant3 | Quadrant4